## Sheet1
Phase | Purpose | Key Activities | Documentation / Deliverables
1. Initiate Program | Establish commitment and build awareness | Define objectives; Gain executive sponsorship; Identify stakeholders | Implementation Charter; Stakeholder Map; Communication Plan
2. Define Problems and Opportunities | Understand drivers and current issues | Identify pain points; Assess current maturity; Define goals | Assessment Report; Problem Statement; Business Case
3. Define Roadmap | Plan initiatives and prioritise improvements | Set priorities; Identify quick wins; Sequence steps | Improvement Roadmap; Prioritisation Matrix; Budget Plan
4. Plan Implementation | Develop concrete implementation plan | Assign responsibilities; Define KPIs; Develop plans | Implementation Plan; Risk Register; KPI Document
5. Execute Improvements | Carry out governance improvements | Execute process/control improvements; Monitor progress | Change Logs; Updated Policies; Progress Reports
6. Sustain Improvements | Embed changes in culture and practice | Build continuous improvement; Train stakeholders | Training Materials; Operating Procedures; Updated RACI
7. Evaluate, Monitor, and Adjust | Assess impact and refine | Evaluate performance; Monitor KPIs; Refine controls | Post-Implementation Review; Lessons Learned; Governance Model