## Sheet1
Phase | Purpose | Key Activities | Documentation / Deliverables | Responsible Role
1. Starting up a Project | Ensure prerequisites for initiating are in place | Appoint executive and PM; Capture previous lessons; Create outline Business Case | Project Brief; Daily Log; Outline Business Case; Project Product Description | Project Manager / Executive
2. Initiating a Project | Establish solid foundation for the project | Refine Business Case; Create Project Plan; Identify controls | PID (Project Initiation Documentation); Risk Register; Communication Plan | Project Manager
3. Directing a Project | Provide overall direction and decision-making | Approve project initiation, stages, exceptions; Communicate with stakeholders | Highlight Reports; Exception Reports; End Stage Reports | Project Board (Executive, Senior User, Senior Supplier)
4. Controlling a Stage | Day-to-day control of project activities | Authorise work packages; Monitor stage progress; Report exceptions | Work Packages; Issue Reports; Checkpoint Reports; Product Status Account | Project Manager
5. Managing Product Delivery | Ensure agreed work packages are delivered | Accept, execute and deliver work packages | Team Plans; Product Descriptions; Quality Register | Team Manager
6. Managing Stage Boundaries | Prepare for the next stage | Review stage performance; Plan next stage; Update Business Case | Stage Plan; End Stage Report; Updated Business Case | Project Manager
7. Closing a Project | Provide a controlled and orderly project closure | Evaluate project; Obtain acceptance; Archive records | End Project Report; Lessons Log; Follow-on Action Recommendations | Project Manager / Project Board