## Sheet1
Process/Element | Responsible | Accountable | Consulted | Informed
Starting Up a Project | Project Manager | Executive | Project Assurance | Stakeholders
Initiating a Project | Project Manager | Project Board | Users, Suppliers | Stakeholders
Directing a Project | Project Board | Executive | Project Manager | Stakeholders
Controlling a Stage | Project Manager | Project Board | Team Manager | Project Board
Managing Product Delivery | Team Manager | Project Manager | Project Manager | Project Manager
Managing a Stage Boundary | Project Manager | Project Board | Users, Suppliers | Stakeholders
Closing a Project | Project Manager | Project Board | Users, Suppliers | Stakeholders
Business Case | Project Manager | Executive | Users, Suppliers | Stakeholders
Plans | Planning Team | Project Board | Finance, Stakeholders | Stakeholders
Risk Management | Project Support | Executive | Risk Owner | Project Board
Quality Management | Quality Assurance | Executive | Users | Stakeholders
Change Control | Change Authority | Project Board | Project Manager | Stakeholders
Progress Control | Project Support | Project Board | Project Manager | Stakeholders